## Executive Summary
Master Data Entity Metadata Review
Prepared 2026-05-16. Static review; final counts require DB-backed audit.
Area | Summary | Current Status | Next Action
Review scope | Master-data entity registry, entity versions, entity fields, display metadata, enum/reference configuration, and runtime contract alignment. | Static review completed from SQL/TypeScript sources. | Run the DB-backed audit after a clean seed to produce the final field-by-field backlog.
Primary risk | Metadata can drift from physical master tables/views: missing entity registrations, stale column mappings, invalid field data types, incomplete enum/reference metadata, and unsafe editability flags. | Preliminary issues identified; exact counts require seeded DB confirmation. | Implement verification script and fail CI on invalid metadata.
Runtime dependency | The compiler reads version-bound control.entity_field rows; canonical dictionary rows are not merged into runtime output. | Version-bound fields are the authoritative source for rendered fields. | Audit every active entity version, not only canonical dictionary seed files.
Known blocker | Local database athyper_dev1 was unavailable during this review. | server/db db:setup:status failed because database athyper_dev1 does not exist. | Create or point DATABASE_ADMIN_URL to a seeded local database, then run Phase 0 audit.
Recommended delivery | Treat the cleanup as a metadata quality program: audit, normalize contracts, register/exclude all relations, repair fields table by table, then harden CI. | Workplan prepared. | Start with global type normalization and entity coverage decisions.
Note on A5: Static report generated from source review. Run the DB-backed audit before applying patches.

## Static Findings
Static Findings
Preliminary source findings. Confirm against a clean, post-seed database before patching.
ID | Severity | Finding | Evidence / Examples | Impact | Recommended Action
F-001 | High | Entity/table coverage is incomplete or not explicitly governed. | Examples: party_risk_assessment, risk_model, tenant_risk_source_config, intercompany_trading_pair, business_partner_relation, network_provider, tenant_parameter_definition, record_bookmark, trusted_device. | Tables may be unavailable to generic list/detail/reference/import/export runtimes, or may be unmanaged by metadata quality checks. | For every master relation, register as runtime entity, register as read-only/internal, or add to an explicit exclusion list.
F-002 | High | View and projection entities need first-class backing rules. | v_business_partner_address, v_business_partner_app_index, v_business_partner_bank_account, v_business_partner_role_summary, supplier_app_index, customer_app_index. | Projection fields may be treated as writable base fields, causing record write failures or confusing edit surfaces. | Use consistent backing_type/read-only feature flags and verify fields against projection columns.
F-003 | High | Invalid or non-contract data types appear in seed sources. | timestamp appears in broad master field seeds; enum[] appears in domain registration rows. API contract accepts datetime/timestamptz and known array types. | Compiled metadata can fail schema validation or reach renderers with unknown field types. | Replace timestamp with timestamptz/datetime. Replace enum[] with text_array plus enum_domain_code, or add a formal enum_array type end to end.
F-004 | High | Column mapping drift still needs DB-backed proof after patch seeds. | 099_fix_entity_field_column_mappings.sql repairs many stale mappings and deletes orphan fields. | Source INSERT inspection alone can report false positives or miss post-patch drift. | Run the audit against post-seed effective rows and treat that as the authoritative backlog.
F-005 | Medium | Reference fields are inconsistently configured. | Some reference-like fields use validation.ref_entity, some use reference_config, and some rely on naming convention. | Pickers, display labels, dependent filters, and navigation can be inconsistent or broken. | Populate reference_config.target_entity, target/display fields, and picker config for all visible references.
F-006 | Medium | Enum fields need stable domains. | Some broad seed rows use empty enum_config placeholders. | Dropdowns cannot reliably resolve options and domain ownership is unclear. | Prefer enum_domain_code = master.<domain>; reserve inline enum_config for complete static sets only.
F-007 | Medium | Required/editability flags need semantic review. | SQL nullability, generated columns, defaulted fields, lifecycle fields, audit fields, and projection fields require different runtime behavior. | Forms can block on non-user fields or allow edits to trigger-maintained/read-model fields. | Review flags field by field; make generated/audit/projection fields read-only and hide as appropriate.

## Field Checklist
Field-By-Field Checklist
Use this checklist for every active control.entity_field row on master entities.
Property | Required Review | Pass Criteria | Owner / Notes
name | Stable logical field name; no duplicate semantic aliases unless intentional. | Unique per entity version; naming matches runtime and domain language.
column_name | Exists on backing table/view, or field is explicitly computed/projection-only. | DB audit returns zero missing columns for non-computed active fields.
label | Human-readable and domain-specific. | No raw snake_case labels in visible fields.
description | Present for non-obvious governance, finance, tax, risk, and integration fields. | High-impact fields have descriptions.
data_type | One of the lookup/API contract values. | No timestamp or ad hoc enum[] values unless contract is extended.
ui_type | Matches renderer behavior. | Uses known controls such as text, textarea, select, date, datetime, reference, money, checkbox, hidden, status, json.
cardinality | Aligns with SQL nullability and business semantics. | one, zero_or_one, or many only.
origin | Correct source classification. | system for engine/audit/FK infrastructure; standard for shipped business fields; business only for tenant custom fields.
is_required | Business/form requirement, not blind SQL nullability. | Defaulted/generated system fields do not block forms; true business-required fields are marked.
is_unique / unique_scope | Matches unique constraints and natural keys. | Scope is populated when is_unique is true and field is user-meaningful.
is_searchable | Only useful search fields. | Limited to code/name/text/search-vector style fields.
is_filterable | Only fields that should appear in filters/facets. | Enums, status, references, dates, and common categorical fields reviewed.
is_sortable | Backed by sortable column and useful order. | Default sort fields are sortable and indexed where needed.
is_read_only | True for generated/audit/projection/trigger-maintained fields. | Writable forms exclude read-only fields.
is_computed / compute_mode | Required for fields not persisted on the registered relation. | Computed fields have compute mode and are not treated as writable columns.
enum_domain_code | Required for domain enum fields unless inline config is complete. | No empty enum_config placeholders for domain data.
reference_config | Required for visible references. | target_entity, target_field/display_field, and picker config set where needed.
validation | Ranges, max lengths, ref hints, date windows, formats. | Validation mirrors DDL/domain constraints where runtime needs it.
default_value | Matches DB default where forms should prefill. | No misleading defaults for system-populated fields.
ui_hint | Group key, display section, badges, visibility hints. | Detail forms and list views have predictable grouping/order.
visibility / editability | Matches lifecycle, role, and surface behavior. | No editable projection/audit fields; lifecycle restrictions honored.
lookup_config / lookup_profile | Dependent pickers and filtered references. | Company-scoped and parent-dependent references filter correctly.
sort_order | Stable and grouped. | No confusing collisions in primary form/list sections.

## Workplan
Update Workplan
Recommended remediation sequence from audit to CI hardening.
Phase | Objective | Activities | Deliverables | Exit Criteria
0 | Build authoritative audit. | Create server/db/scripts/verify-master-entity-metadata.ts. Run after clean DDL plus platform seed. Compare entity registry, active fields, display config, enum/reference config, and editability. | DB-backed audit workbook/CSV plus JSON issue output. | Audit runs repeatably and produces a prioritized backlog.
1 | Normalize global field contracts. | Replace timestamp metadata. Resolve enum[] representation. Make common audit fields consistent. | Patch seed files and contract/schema changes if required. | No invalid data_type values in DB audit.
2 | Align entity registry coverage. | Classify every master relation as runtime, read-only/internal, projection/view, or excluded. Update control.entity rows and exclusion manifest. | Entity coverage patch plus exclusion list. | No unexplained master relation is missing from registry/exclusion.
3 | Fix field mappings table by table. | Batch by domain: identity, finance, BP, banking, products, people, risk/intercompany/parameters. Fix column_name, type, UI, required/read-only, enum/reference config, display config. | Domain-specific seed patches. | Missing-column and unmapped-column audits are clean or explicitly waived.
4 | Harden runtime validation. | Add CI checks for invalid types, missing columns, broken display config refs, enum/reference gaps, and writable projection fields. | CI verifier integrated into db/server checks. | CI fails on metadata drift.
5 | Verify runtime behavior. | Run clean seed, Prisma validate/generate, compiled metadata smoke, list/detail smoke, and reference picker smoke. | Verification logs and residual risk list. | Every active master entity compiles and core routes smoke successfully.

## Coverage Candidates
Coverage Candidates
Examples from static review. Final list must come from the DB-backed audit.
Relation / Entity | Category | Current Review Signal | Decision Needed
party_risk_assessment | Party risk | Master DDL relation without obvious runtime entity registration in static review. | Register, mark internal/read-only, or exclude.
party_risk_dimension_score | Party risk | Master DDL relation without obvious runtime entity registration in static review. | Register, mark internal/read-only, or exclude.
party_risk_driver | Party risk | Master DDL relation without obvious runtime entity registration in static review. | Register, mark internal/read-only, or exclude.
party_risk_mitigation | Party risk | Master DDL relation without obvious runtime entity registration in static review. | Register, mark internal/read-only, or exclude.
party_risk_review_event | Party risk | Master DDL relation without obvious runtime entity registration in static review. | Register, mark internal/read-only, or exclude.
risk_dimension | Party risk reference | Master DDL relation without obvious runtime entity registration in static review. | Register as reference/control data or exclude.
risk_model | Party risk config | Master DDL relation without obvious runtime entity registration in static review. | Register as managed config or exclude.
tenant_risk_source_config | Party risk config | Master DDL relation without obvious runtime entity registration in static review. | Register as tenant config or exclude.
intercompany_trading_pair | Intercompany | Master DDL relation without obvious runtime entity registration in static review. | Register as operational master or exclude.
business_partner_relation | BP hardening | Master DDL relation without obvious runtime entity registration in static review. | Register as BP child/relation entity or exclude.
business_partner_network_capability | BP network | Master DDL relation without obvious runtime entity registration in static review. | Register as child entity or exclude.
network_provider | BP network reference | Master DDL relation without obvious runtime entity registration in static review. | Register as reference data or exclude.
tenant_parameter_definition | Tenant parameters | Master DDL relation without obvious runtime entity registration in static review. | Register as config entity or exclude.
tenant_parameter_value | Tenant parameters | Master DDL relation without obvious runtime entity registration in static review. | Register as config entity or exclude.
record_bookmark | Collaboration extension | Master DDL relation without obvious runtime entity registration in static review. | Probably internal; add explicit exclusion if not runtime-visible.
filter_preset | Collaboration extension | Master DDL relation without obvious runtime entity registration in static review. | Probably user preference/runtime config; decide ownership.
trusted_device | Identity/security | Master DDL relation without obvious runtime entity registration in static review. | Likely internal/security; register read-only or exclude.
v_business_partner_address | Projection/view | Entity should be verified against view columns and read-only behavior. | Mark view/projection semantics consistently.
v_business_partner_app_index | Projection/view | Entity should be verified against view columns and read-only behavior. | Mark view/projection semantics consistently.
v_business_partner_bank_account | Projection/view | Entity should be verified against view columns and read-only behavior. | Mark view/projection semantics consistently.
v_business_partner_role_summary | Projection/view | Entity should be verified against view columns and read-only behavior. | Mark view/projection semantics consistently.

## Audit SQL
Audit SQL
Queries to implement in the DB-backed verification script.
Audit | Purpose | SQL | Expected Result
Missing backing relation | Find control.entity rows whose table/view does not exist. | WITH rels AS ( SELECT table_schema, table_name, 'table' AS rel_kind FROM information_schema.tables WHERE table_schema = 'master' UNION ALL SELECT table_schema, table_name, 'view' AS rel_kind FROM information_schema.views WHERE table_schema = 'master' ) SELECT e.entity_code, e.backing_type, e.table_schema, e.table_name FROM control.entity e LEFT JOIN rels r ON r.table_schema = e.table_schema AND r.table_name = e.table_name WHERE e.table_schema = 'master' AND e.tenant_id IS NULL AND r.table_name IS NULL ORDER BY e.entity_code; | Zero rows, except intentional virtual entities on an approved exclusion list.
Missing field column | Find active non-computed fields whose column does not exist on the backing relation. | WITH cols AS ( SELECT table_schema, table_name, column_name FROM information_schema.columns WHERE table_schema = 'master' ) SELECT e.entity_code, e.backing_type, e.table_name, ef.name, ef.column_name, ef.data_type FROM control.entity e JOIN control.entity_version ev ON ev.entity_id = e.id AND ev.status = 'EFFECTIVE' JOIN control.entity_field ef ON ef.entity_version_id = ev.id AND ef.is_active = true LEFT JOIN cols c ON c.table_schema = e.table_schema AND c.table_name = e.table_name AND c.column_name = ef.column_name WHERE e.table_schema = 'master' AND e.tenant_id IS NULL AND COALESCE(ef.column_name, '') <> '' AND COALESCE(ef.is_computed, false) = false AND c.column_name IS NULL ORDER BY e.entity_code, ef.sort_order, ef.name; | Zero rows after computed/projection fields are modeled correctly.
Invalid data types | Find field data types outside the lookup/API contract. | SELECT e.entity_code, ef.name, ef.column_name, ef.data_type FROM control.entity e JOIN control.entity_version ev ON ev.entity_id = e.id AND ev.status = 'EFFECTIVE' JOIN control.entity_field ef ON ef.entity_version_id = ev.id AND ef.is_active = true LEFT JOIN control.lookup_value lv ON lv.domain_code = 'entity_field.data_type' AND lv.code = ef.data_type AND lv.tenant_id IS NULL WHERE e.table_schema = 'master' AND e.tenant_id IS NULL AND lv.code IS NULL ORDER BY e.entity_code, ef.name; | Zero rows. Especially no timestamp or enum[] unless formally added to the contract.
Enum/reference completeness | Find enum/reference-like fields missing domain or target metadata. | SELECT e.entity_code, ef.name, ef.column_name, ef.data_type, ef.ui_type, ef.enum_domain_code, ef.enum_config, ef.reference_config, ef.validation FROM control.entity e JOIN control.entity_version ev ON ev.entity_id = e.id AND ev.status = 'EFFECTIVE' JOIN control.entity_field ef ON ef.entity_version_id = ev.id AND ef.is_active = true WHERE e.table_schema = 'master' AND e.tenant_id IS NULL AND ( (ef.data_type = 'enum' AND ef.enum_domain_code IS NULL AND ef.enum_config IS NULL) OR ((ef.column_name LIKE '%\_id' ESCAPE '\' OR ef.ui_type = 'reference') AND ef.reference_config IS NULL AND NOT (ef.validation ? 'ref_entity')) ) ORDER BY e.entity_code, ef.name; | Zero rows for visible runtime fields; approved internal exceptions documented.

## Sources
Sources
Files and directories used to prepare this workbook.
Source | Role In Review
docs/master-data-entity-metadata-review.md | Narrative report and workplan source.
server/db/ddl/master | Physical master schema: tables, views, triggers, RLS, indexes, constraints.
server/db/seed/010_platform/004_entity_engine/020_entities | Broad platform master entity registrations.
server/db/seed/010_platform/004_entity_engine/035_version_fields | Version-bound field definitions and field mapping repair patches.
server/db/seed/010_platform/005_domain_registrations/100_master | Business partner, supplier, customer, and company-code domain registrations.
server/db/ddl/control/01_tables.sql | Definitions for control.entity, control.entity_version, and control.entity_field.
packages/shared/data/api-contracts/src/schemas/metadata.ts | Runtime API contract for compiled entity and field metadata.
server/framework/runtime/services/metadata/routes/compiled-entity.route.ts | Compiled metadata route and field mapping into API contract shape.